## Summary
Eye-Blink Authentication System - Defect Summary
Total defects logged | 11
Critical | 2
High | 3
Medium | 6
Low | 0
All defects were identified through manual source-code review and, where marked 'Automated', confirmed by an automated test in the QA suite (see TEST_CASES.xlsx 'Linked Test Case' column). Entries marked UNVERIFIED in their Actual column still need a first live run against your local Flask + MySQL instance to confirm.

## Defect Log
Defect ID | Module | Title | Description | Steps to Reproduce | Expected | Actual | Severity | Priority | Status | Linked Test Case
BUG-01 | Signup | /signup blocks the Flask server on a native OpenCV camera window | app.py's /signup handler calls capture_face_samples(), which opens a blocking cv2.VideoCapture(0) + cv2.imshow()/cv2.waitKey() loop directly inside the request handler, waiting for a physical 's' keypress in a native window on whatever machine is running the Flask process. | 1. Run the app 2. Submit a fully valid /signup form (name, email, numeric blink_count) 3. Observe the server process | Face capture should happen client-side (as it does on /login) so the request completes normally and the app can be deployed to a server with no physical webcam attached. | The Flask worker thread blocks until someone at the server's own keyboard/monitor presses 's' 8 times or 'q'. In any real deployment (no local camera, no one watching the server), the request hangs indefinitely and ties up a worker. | Critical | P1 | Open | TC-SU-01
BUG-02 | Signup / Login | Inconsistent face-capture architecture between Signup and Login | Signup captures the face server-side via OpenCV (see BUG-01). Login captures the face client-side in the browser (getUserMedia + canvas, sent as a base64 'face_image' field). | Compare capture_face_samples() in app.py (used by /signup) with blink.js's browser-side capture (used by /login). | Both flows should use the same capture mechanism for consistency and deployability. | Two different, incompatible architectures for what should be the same capability - the signup path cannot work at all once deployed away from the developer's own machine. | High | P1 | Open | TC-SU-01, TC-LG-01
BUG-03 | File Management | IDOR - /download/<email>/<filename> has no authentication check | Every other protected route (/dashboard, /files, /upload) checks `if "user_email" not in session` before proceeding. /download does not. | 1. With no login and no session cookie, send GET /download/<any_known_email>/<any_known_filename> 2. Observe the response | Should redirect to /login (401/302) like every other protected route, and should verify the requester's session email matches the folder being requested. | The file is returned directly with HTTP 200 - any user's uploaded files can be downloaded by anyone who knows or guesses their email and a filename. No login required at all. | Critical | P1 | Open | TC-SEC-06
BUG-04 | Signup | No UNIQUE constraint on users.email in the live schema | db/blinkauth.sql's CREATE TABLE for `users` does not declare email as UNIQUE, unlike the commented-out init_db() function in app.py which does. The signup handler still relies on catching an IntegrityError to show 'Email already exists.' | 1. Import db/blinkauth.sql as-is 2. Sign up twice with the same email | Second signup should be rejected with 'Email already exists. Try logging in.' | UNVERIFIED without a live run, but per the schema as shipped, no IntegrityError will be raised, so the duplicate-email branch is likely unreachable and two rows with the same email can both be inserted. | High | P1 | Open | TC-SU-06
BUG-05 | Login | Security-notification email is non-functional (hardcoded placeholder credentials) | sendemail() hardcodes 'your-email@gmail.com' / 'your-app-password-here' as SMTP credentials. It IS called on face mismatch and blink mismatch to notify the account owner of a failed access attempt. | 1. Trigger a face or blink mismatch on /login 2. Check server logs | An alert email should be sent to the account owner. | smtplib.SMTP.login() will fail with the placeholder credentials; the exception is caught and only printed to the console. The account owner is never actually notified of a failed login attempt, silently defeating a security feature. | Medium | P2 | Open | TC-LG-06, TC-LG-07
BUG-06 | Signup / Login | No CSRF protection on Signup or Login forms | Neither form includes a CSRF token, and Flask-WTF/CSRF protection is not configured in app.py. | 1. Inspect the rendered HTML of /signup and /login for a hidden csrf token field | A per-session CSRF token should be present and validated server-side. | No token is present or checked - both forms are vulnerable to Cross-Site Request Forgery. | Medium | P2 | Open | TC-SEC-01, TC-SEC-02
BUG-07 | Login | Unhandled FileNotFoundError if ref_embed.pkl doesn't exist yet | login() does `with open(REF_EMBED_PATH, "rb") as f: embed_dict = pickle.load(f)` with no existence check and no try/except, unlike signup's more defensive pickle-loading pattern. | 1. On a fresh checkout/DB where no one has ever signed up (ref_embed.pkl absent) 2. Attempt to log in with any email + blink_count + face_image | Should show a graceful message, e.g. 'No face registered for this email.' | Raises an unhandled FileNotFoundError, returning Flask's generic HTTP 500 page instead of a flash message. | Medium | P2 | Open | TC-SEC-08
BUG-08 | Login | Unhandled ValueError when face_image has no comma | get_encoding_from_base64() does `header, encoded = image_data.split(",", 1)` with no guard for a string that contains no comma at all. | 1. POST to /login with face_image='not-a-data-url' (any value with no comma), a valid registered email, and a numeric blink_count | Should show a graceful error, e.g. 'Face not detected properly.' | Raises an unhandled ValueError ('not enough values to unpack'), returning HTTP 500. | Medium | P2 | Open | TC-SEC-07
BUG-09 | Login | Blink count is a client-trusted value, not a server-verified measurement | The browser counts blinks via MediaPipe FaceMesh and sends only the final integer in a hidden field (#blinkInput). The server just compares two integers - it never verifies the submitted count came from real, live blink detection. | 1. Log in far enough to reach the camera step 2. Edit the hidden #blinkInput value via browser dev tools to match the account's stored blink_count 3. Submit without actually blinking | The second factor should be tied to a live, server-verifiable signal, not a client-reported number. | UNVERIFIED live (needs a real registered account to fully confirm), but by design the server-side check (`int(blink_count) != int(user['blink_count'])`) cannot distinguish a genuine blink sequence from a manually-edited field - the second factor can likely be spoofed by anyone with browser dev tools. | High | P1 | Open | TC-LG-08
BUG-10 | File Management | No file type, extension, or size validation on /upload | The /upload handler saves request.files['file'] directly with its original filename and no checks on extension, MIME type, content, or size. Flask's MAX_CONTENT_LENGTH is not set. | 1. Log in 2. Upload an executable, script, or a very large file | Should enforce an allow-list of extensions/MIME types and a reasonable max file size. | Any file type of any size (up to server/OS/disk limits) is accepted and stored as-is under static/uploads/<email>/ - a path that is also directly web-servable and unauthenticated (compounds BUG-03). | Medium | P2 | Open | TC-FILE-03, TC-FILE-04
BUG-11 | Configuration | Hardcoded Flask secret key and DB credentials in source | app.secret_key is a hardcoded string literal, and dbconnection() hardcodes host/user/password rather than reading from environment variables or a config file. | Read app.py lines defining `app.secret_key` and `dbconnection()` | Secrets should come from environment variables / a secrets manager, never committed to source. | A hardcoded, guessable secret key can allow forging signed session cookies; committing DB credentials to source is a standard security anti-pattern flagged in any code review. | Medium | P2 | Open | N/A - found via code review